## Sheet1
Project Timesheet | [19 empty] | WCPM
Name: |  |  | Team: | [13 empty] | Week commencing: |  | 2000-09-04
|  | Work in hours | [7 empty] | Work in days | [6 empty] | Status (NS,S,C) | Est completion date | Planned completion date | Variance
Ref | Description | Mo | Tu | We | Th | Fr | Sa | Su | Total this week | Days B/F | Days this week | To date | Est work remaining | Est total work | Budget | Variance
[9 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  |  | 0
1.1 | Prepare Project Definition | 6 | 5 | 4 |  |  |  |  | 15 | 5 | 1.875 | 6.875 |  | 6.875 | 10 | 3.125 | Complete | 2000-09-06 | 2000-09-15 | 9
1.2 | Agree Project Definition | 2 | 3 | 4 | 12.5 | 8 | 4 | 0 | 33.5 | 1.25 | 4.1875 | 5.4375 | 5 | 10.4375 | 10 | -0.4375 | Started | 2000-09-29 | 2000-09-22 | -7
1.3 | Communicate Project Definition | [7 empty] | 0 |  | 0 | 0 | 10 | 10 | 10 | 0 | Not started | 2000-10-31 | 2000-10-31 | 0
[9 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  |  | 0
[9 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  |  | 0
[9 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  |  | 0
[9 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  |  | 0
[9 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  |  | 0
[9 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  |  | 0
[9 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  |  | 0
[9 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  |  | 0
[9 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  |  | 0
[9 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  |  | 0
[9 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  |  | 0
[9 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  |  | 0
[9 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  |  | 0
[9 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  |  | 0
[9 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  |  | 0
[9 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  |  | 0
[9 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  |  | 0
|  | 8 | 8 | 8 | 12.5 | 8 | 4 | 0 | 48.5 | 6.25 | 6.0625 | 12.3125 | 15 | 27.3125 | 30 | 2.6875
Issues | [12 empty] | Deliverables |  |  |  |  | Completion date
Ref | Title | Comments | [10 empty] | Ref | Title |  |  | Status | Estimated | Planned | Variance
1 | Interface to commission | New issue - need interface to the Commission system | [11 empty] | Draft Project Definition |  |  | Complete | 2000-09-06 | 2000-09-15 | 9
[14 empty] | Final Project Definition |  |  | Started | 2000-09-29 | 2000-09-22 | -7
0
0
0
0
0
0